## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Light
PROJECT: Light
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Riku Nakano
Project start date: | 2025-03-27 |  |  |  |  | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2025-04-01 to 2025-05-26
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-04-01 to 2025-05-26
Project development
Project charter | Goal | Name | 25% | 2025-03-27 | 3
Research | Milestone |  |  | 2025-04-01 | 1 | bar: 2025-04-01
Projections | Low Risk |  | 50% | 2025-03-24 | 10
Stakeholders | Milestone |  |  | 2025-04-16 | 1 | bar: 2025-04-16
Review | Med Risk |  | 10% | 2025-04-02 | 6
Contracts
Proposals | High Risk |  | 60% | 2025-04-02 | 13
Document review | On Track |  | 50% | 2025-04-04 | 9
Bid date | Low Risk |  | 33% | 2025-04-09 | 11
Award date | Milestone |  |  | 2025-04-11 | 1 | bar: 2025-04-11
Finalize |  |  |  | 2025-04-12 | 24
Design
Feasibility study | On Track |  |  | 2025-04-11 | 4
Submit permit applications | Med Risk |  |  | 2025-04-14 | 14
Design proposal | On Track |  |  | 2025-04-29 | 6
Materials | Goal |  |  | 2025-05-03 | 3 | 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2
Equipment | Low Risk |  |  | 2025-04-02 | 19
Testing
Environment |  |  |  | 2025-05-06 | 15
System test |  |  |  | 2025-05-20 | 5
Issues/bugs | Milestone |  |  | 2025-07-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
System automatycznej realizacji zamówień
Politechnika Poznańska |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Michał Borowski, Tadeusz Bugalski, Jakub Czerwiński
Project start date: | 2025-03-13 |  |  |  |  | March | [13 empty] | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2025-03-18 to 2025-05-16
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Projekt Regału
Projektowanie + Wymiarowanie elementów 3D | On Track | JC, TB | 75% | 2025-03-13 | 20
Dobór elementów konstrukcyjnych | Low Risk | JC, TB | 50% | 2025-03-21 | 21
Skompletowanie elementów | Low Risk | JC, TB, MB | 50% | 2025-04-07 | 7
Wydruk Elementów 3D | Med Risk | JC, TB, MB | 0% | 2025-04-07 | 5
Schemat Elektryczny | Low Risk | JC, TB | 0% | 2025-04-02 | 12
Montaż fizyczny regału | High Risk | JC, TB, MB | 0% | 2025-04-14 | 10
Projekt PLC
Symulacja programu PLC | On Track | JC, TB | 0% | 2025-04-23 | 4
Montaż szafy sterowania | Med Risk | JC, TB | 0% | 2025-04-27 | 7
Integracja szafy sterowniczej z regałem | High Risk | JC, TB | 0% | 2025-05-04 | 2
Próba generalna | Milestone |  |  | 2025-05-06 | 1 | bar: T
Projekt webservera (Backend)
Struktura bazy danych (modele, architektura) | Low Risk | MB | 0% | 2025-03-28 | 3
Moduł składania zamówień i ich śledzenia | Med Risk | MB | 0% | 2025-03-31 | 5
Tworzenie, edycja i usuwanie zamówień | Low Risk | MB | 0% | 2025-04-05 | 5
API do komunikacji z PLC (snap7) | Med Risk | MB | 0% | 2025-04-10 | 3
Logowanie operacji i błędów | Low Risk | MB | 0% | 2025-04-13 | 5
Testy API (postman, Jest) | Low Risk | MB | 0% | 2025-04-18 | 5
Projekt webservera (Frontend)
Makieta w Figma | Low Risk | MB | 0% | 2025-04-25 | 2
Obsługa autoryzacji użytkownika | Med Risk | MB | 0% | 2025-04-27 | 3
UI Do składania zamówień | Low Risk | MB | 0% | 2025-04-30 | 3
UI do dodawania produktów | Low Risk | MB | 0% | 2025-05-03 | 3
UI do wyświetlania poprzednich zamówień i paczek | Med Risk | MB | 0% | 2025-05-06 | 5
Dokumentacja projektu
Dokumentacja dla developerów (Serwer + Frontend) | Low Risk | MB | 0% | 2025-05-11 | 5
Dokumentacja Regału | Low Risk | MB, TB, JB | 0% | 2025-05-11 | 5
Dokumentacja programu PLC | Low Risk | TB, JB | 0% | 2025-05-16 | 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT: Color
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2025-03-27 |  |  |  |  | April | [34 empty] | May
Scrolling increment: | 5 | time axis 2025-04-01 to 2025-05-26
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2025-04-01 to 2025-05-26
TITLE 1
Task 1 | Goal | Name | 25% | 2025-03-27 | 3
Task 2 | Milestone |  |  | 2025-04-01 | 1 | bar: 2025-04-01
Task 3 | Low Risk |  | 50% | 2025-03-24 | 10
Task 4 | Milestone |  |  | 2025-04-16 | 1 | bar: 2025-04-16
Task 5 | Med Risk |  | 10% | 2025-04-02 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2025-04-02 | 13
Task 2 | On Track |  | 50% | 2025-04-04 | 9
Task 3 | Low Risk |  | 33% | 2025-04-09 | 11
Task 4 | Milestone |  |  | 2025-04-11 | 1 | bar: 2025-04-11
Task 5 |  |  |  | 2025-04-12 | 24
TITLE 3
Task 1 | On Track |  |  | 2025-04-11 | 4
Task 2 | Med Risk |  |  | 2025-04-14 | 14
Task 3 | On Track |  |  | 2025-04-29 | 6
Task 4 | Goal |  |  | 2025-05-03 | 3 | 2025-05-03: 2; 2025-05-04: 2; 2025-05-05: 2
Task 5 | Low Risk |  |  | 2025-04-02 | 19
TITLE 4
Task 1 |  |  |  | 2025-05-06 | 15
Task 2 |  |  |  | 2025-05-20 | 5
Task 3 | Milestone |  |  | 2025-07-01 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one